## Sheet1
Group No: 3 Poornima College of Engineering Department of Information Technology Product Backlog (Product-II:2018-19)
Epic | Sprint | User story role | User story name | Story Details | Tasks Items | Analyst/Prep Work/Documentation | Dev. Estimation | QA | Total User Story Hours
Online Banking System | 1 | Admin | Create a registration page for each customer for online banking | As an admin, There are several customer. Each customer provide one page to register themselves on the portal. If once register the portal customer can access their details. | 1. Develop a template for the registration page. 2. Fill all the required registration details from the customer. 3. Documentation | 3 | 10 | 5 | 18
Online Banking System | 2 | Admin | Create a registration page for customers for non account holders | As an admin, there are several new customers .Each new customer provide one page to create account . | 1. Develop a template for the registration page. 2. Updation of registration database. | 3 | 12 | 7 | 22
Online Banking System | 3 | Admin | Create a login page for all registered customer | As an admin, for each registered customer there will be a login page to log in to portal. | 1. Develop a template for the login page. 2. Fill out the log in details from the customer. 3. Login customers can successfully visit home page | 3 | 9 | 5 | 17
Online Banking System | 4 | Admin | Create Main Home Page | As an admin, Every customer see the records. | 1. Define the look and the feel of the web page. 2.Every login customer can access the home page. 3. Link all the other pages to the home pages. | 4 | 13 | 11 | 28
Online Banking System | 5 | Admin | Database Connectivity | As an Admin, Registered customer details are stored in the database and fetched at the time of login. | 1. Details from the registrstion page are stored in the database. 2.Create database tables with fields. . 3. Store the information into the fields. 4. Fetched the login details from the database. | 6 | 20 | 20 | 46
Online Banking System | 6 | customer | Showcase account summary | As a customer , can acess the portal to get their account summary. | 1. Create a link for the account summary. . 2. Fetch the account summary from the Database. | 3 | 8 | 7 | 18
Online Banking System | 7 | customer | Fund transfer | As a customer , customer will able to transfer the money to another account . | 1. Create a link for the fund transfer 2. Develop a template the fund transfer portal 3. Update the database | 6 | 20 | 7 | 33
Online Banking System | 8 | customer | Update personal detail | As a customer, customer update the personal deatils . | 1. Create a link for the personal deatils 2. Update the personal details within Database. 3. Fetch the personal details from database. | 6 | 10 | 10 | 26
Online Banking System | 9 | customer | Contact Us | As an customer,can contact with the bank through mail | 1.Create a link for the contact us 2. Develop a templet contact us page | 5 | 12 | 12 | 29
Online Banking System | 10 | customer | Logout | As an customer, customer can logout their id | 1. Create a link for the logout | 4 | 8 | 10 | 22
Online Banking System | 10 | Admin | Link all the other web pages with main page. | As an admin, all the separate pages connected to main page. | 1. Connect all the webpages. 2. Testing | 4 | 10 | 18 | 38
Total | [5 empty] | 47 | 132 | 112 | 297
(Pradeep Natani) Project Guide |  |  |  | (Shubham Dixit) Scrum Master |  | (Shirish Nagar) Project Coordinator